## Plan
SLP REQUIREMENTS GATHERING
DELIVERABLE: Consolidated list of requirements with assessed priority and/or weighted importance
TARGET COMPLETION DATE: June 30
| Stream Lead: Manasi Mankame |  |  |  | Timeline
| What the color coding means: | Planned and on track | Completed
| Task | Responsible | Status | Progress | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25 | 2016-06-26 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01 | 2016-07-02 | 2016-07-03 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08
1 | Determine who and how to gather the new set of requirements | All | Complete | 100%
2 | Set up user interviews | MM
2.1 | Stakeholder view - Regis, Sarah | Sarah?
Regis C
Sarah O
2.2 | Gather requirements by selected target audiences: Architects & Dev Ops
Review script
| Architects(Interview Lorna and Sally) | Architects
Peer to peer learning
| Dev Ops(Interview Simon and Lorna) - cancelled due to lack of sponsorship | DevOps
Peer to peer learning
2.3 | Review / add / challenge requirements by six learning approaches (include requirements around roles, skillsets, etc.)
Review script
Mindi
Sally
Annette
Barbara
2.4 | Include requirements from Digital Architect and Digital Strategy
Interview Denis Dupriez
Interview Bertrand Cauwet
2.5 | Test the requirements against the new DAL design principles (5)
2.6 | Create the social learning point of view | Shiva
2.7 | Gain input from new Bersin study on social learning | Shiva
2.8 | Document any key questions and assumptions. For example, “when do we require a dedicated SLP for an approach?”
2.9 | Consolidate list of requirements | Manasi
Create empathy map
| Estimate weight and priority for each requirement | Manasi
| validate weights and priorities | Debbie and Shiva
3 | Review consolidated list with stakeholders (trends)
Review final requirements with stakeholders
Note on B12: Mankame, Manasi R: - scope of SLP - offers(economy/ first))
Note on B18: Mankame, Manasi R: Integrate results of Architects focus interviews
Note on B21: Mankame, Manasi R: Details for Architects and Dev Ops
Note on B31: Mankame, Manasi R: Integration and landscape related questions
Note on B32: Mankame, Manasi R: Peer to peer learning lead
Note on AC36: Mankame, Manasi R: Pres to regis and sarah
Note on B38: Mankame, Manasi R: Included in social learning PoV

## Requirements
SOCIAL LEARNING PLATFORM REQUIREMENTS
PRINCIPLES OF REQUIREMENT IDENTIFICATION
1. Requirements captured should be clear and measurable
2. Requirements captured should become valid input for vendor selection
3. Requirements can be categorized into offers to suit specific target audiences
4. What can Yammer do - not addressed directly
5. Identify resourcing and organizational change to make social learning a success
Feature Block | Description |  | Priority(1:nicetohave-5:must have) | Weight
SOCIAL |  |  | 5 | 30
Social | Find/search for an expert, mentor, events and documents/material relevant to a topic(peer to peer), gatherings | 100% of interviewed users said that they would use this information to share content with and by participants. To make learning seamless and continuous, they want to be part of existing conversations
Social | Share: content, experience, knowledge. Share links, documents, videos
Social | Follow: topic, expert, gathering, path, content
Social | Create: communities, channels, content (blog, video, wiki, resource), gatherings
Social | Contribute feedback through likes, rate, recommend, follows, comments & shares; Discussions in subject/ interest groups / gatherings (ask questions, provide answers)
Social | Create or add quizzes to material
Social | Create and publish video and audio casts and other material
Social | Able to identify 'appropriate / best' content through reviews and/or ratings | 100% of users said that the SLP must support curation of content and enable the best content to bubble up to the top through user ratings and reviews.
Social | Links to latest news / RSS feeds
Social | Plug-in' feature to easily share content / websites/ videos
USABILITY |  |  | 5 | 20
Usability | Omni-channel, accessible from desktop, tablet and phone User experience needs to be easy and appealing (no extra sign on, search option) Intuitiveness | The collaboration element of the platform must be supported by functionality and a UX to support leanring at the point of need. To this purpose, functionality enabling anytime anywhere access becomes critical to the platform
PREDICTIVE ANALYTICS |  |  | 5 | 15
Predictive Analytics | Having the data to make recommendations on people and content to collaborate with based on actions, behaviour and engagement See what's trending
ROLES |  |  | 5 | 0
Champion/Community Manager
INTEROPERABILITY |  |  | 4 | 5
Interoperability | Compatibility with other CG platforms Scalability Hosting model Device interoperability
CONFIGURATION and MAINTENANCE |  |  | 3 | 10
Configuration AND Maintenance | Ability to leverage existing groups (Preferred to link to already existing groups/channels)
Configuration AND Maintenance | Functionality to support both continuous and short term programs
Configuration AND Maintenance | Ability to link out to other useful sites
Configuration AND Maintenance | Data Security Session Management & Control SSO integration methods to ensure that only authorized users are allowed to use the application and share the data Security Integration methods to adhere with Capgemini firewalls. This is to ensure data security.
Configuration AND Maintenance | Application Maintenance Version control policies/procedures No downtime during normal business hours Minimal downtime during off hours
Configuration AND Maintenance | Support Services (since the platform will be used by Capgemini corporate account) Support via phone, email and chat User manuals and updates with every version change Training after initial installation for administrators Training (offline/online) after each upgrade for administrators
Configuration AND Maintenance
REPORTING |  |  | 3 | 10
Reporting | Reporting on how are users using the site? Method for collecting feedback and evaluation/ suggestions
PERSONALISATION |  |  | 2 | 5
Personalisation | User profiles available to view and update, with areas of interest, levels of certification. badges etc | Personalisation did not come up much during interviews. This could be because much of the pain today lies in activating and engaging users in social groups. Once users have an active presence in this space, the conversation can move to how users are more effective in their interactions
Personalisation | Ability to specify preferences (alerts, notifications, interest areas, region pereferences)
Personalisation | Dashboard: learning, achievements, activities, connections, communities, gatherings
Personalisation | Personal dynamic development paths
Personalisation | Record of the events, traditional classes, online activity user participanted in
GAMIFICATION |  |  | 2 | 5
Gamification | Earn points and achieve levels/ badges for engagement and completion of content | Gamification is a great tecnique to increase the engagement of users in the social platform. In the users that were interviewed, gamification was intrinsic to the conversation, but did not come up as a burning priority
Gamification | View leader board, filter by region/topic
Gamification | Have Fun , challenge colleagues
Total Cost of Ownership |  |  |  | 0
100
Note on B24: Mankame, Manasi R: amazon.com type functionality where platform is able to suggest recommended resources to users based on their browsing history
Note on B39: Mankame, Manasi R: Identified as an advanced usage behaviour, nice to have now and will become more important as social behaviour evolves
Note on B45: Mankame, Manasi R: Identified as an advanced usage behaviour, nice to have now and will become more important as social behaviour evolves

## Appendix(Archived)
Resources
· Requirements Gathering |  | Manasi , Lead |  | Project Team | Role
DELIVERABLE: Consolidated list of requirements with assessed priority and/or weighted importance |  | Supporting resources | Shiva / Lorna / SMEs / Debbie | Lorna | PM Arch SLP Pilot
TARGET COMPLETION DATE: June 30 |  |  |  | Shiva
o Determine who and how to gather the new set of requirements |  |  |  | Debbie
o Gather requirements by selected target audiences: Architects & Dev Ops |  |  | Denis | Sarah | Sponsor; Learning Approaches SME
o Review / add / challenge requirements by six learning approaches (include requirements around roles, skillsets, etc.) |  |  | Regis / Sarah - C | Bhavin
o Include requirements from Digital Architect and Digital Strategy |  |  | Annette: Fast & Furious (C/I) | Medha | ?
o Test the requirements against the new DAL design principles (5) |  |  | Barbara: Leadership (C/I) | Sally | Architect SME
o Gain input from new Bersin study on social learning |  |  | Shiva | Simon | DevOps SME
o Document any key questions and assumptions. For example, “when do we require a dedicated SLP for an approach?” |  |  | Mindi: LPM | Denis | Digital Architect
o Consolidate list of requirements |  |  | Manasi | Regis | Learning Approaches SME
o Review consolidated list with stakeholders to assign priority / weighting |  |  | Manasi | Sumehga | ?
· Vendor Scan |  | Shiva, Lead
DELIVERABLE: Short-list of preferred vendors (internal (KM3.0, Yammer, and SumTotal 2016) and external) to do comparison analysis against our priorities |  | Supporting resources | Bhavin
TARGET COMPLETION DATE: June 17 |  |  | team- vendor reviews
o Leverage DCX benchmarking as base
o Add vendors identified via Brandon Hall, Gartner, our own recommendations
· Assessment of Vendor Match to Our Requirements |  |  | Debbie ? Sumegha ? Shiva? Lorna?
DELIVERABLE: Identification of top 2-3 vendor recommendations to meet our needs and go into deeper discussion
TARGET COMPLETION DATE: July 8
o Research on vendor products
o Define scale to rate ability to meet our requirements (no, partial, fully ???)
o Assess capability to meet our needs on defined scale
o Add qualitative comments about vendor (market share, other clients, awards / mentions, etc..)
o Perform comparative fit analysis of vendor to our needs
o Identify top 2-3 recommended vendors and why (is business case document required?)
Requirements and fit analysis - need to also look at culture, skill set and roles required.
· Run pilots to test vendor recommendations (pilot selected based on learning approach?) May - Sept |  |  | Lorna
o Dev Ops Pilot |  |  | Lorna
§ Tbd – based on top vendor recommendation
§ Add / adjust our vendor recommendation and “way forward point of view” based on experiences
o Architects Pilot |  |  | Lorna
§ Add / adjust our vendor recommendation and “way forward point of view” based on experiences
o Event Pilot???
o Program Pilot???
· Develop “Way Forward” Recommendation
DELIVERABLE; ExCom proposal, budget
TARGET COMPLETION DATE: Sept