## Slide 1
University 2012 The Transformation Project of the Capgemini University
A monthly update to inform the University Team
July 2010

## Slide 2
1
During the first quarter of 2010, we had the kick off for University 2012, the Transformation Project of the Capgemini University. Since the kick off, a lot of work has been done. To keep everybody within the University team informed about the status of the project, a newsletter will be sent regularly to all team members… This is the first edition!
Maybe you are currently working for a stream within the transformation project. Or maybe you are not actively working for the project. To give everybody the opportunity to understand what University 2012 is about, this newsletter gives you information about:
The objectives of University 2012; - The organization chart of University 2012; - Introduction of the Project Management team; - Status update.
While this issue focuses on giving you the basic information about the project, the next issue will focus more on the updates of the various streams of the project.
If you have any questions after reading this newsletter, please don’t hesitate and contact Simone Kraal (simone.kraal@capgemini.com) or Karan Kalra (karan.kalra@capgemini.com).
Capgemini University 2012
Introduction

## Slide 3
Objectives of University 2012
Capgemini University 2012
2
In 2008 the University got its EFMD accreditation. To get the accreditation it was necessary to do an extensive self-assessment. The self-assessment gave an insight into both the strengths of the University and the aspects which needed improvement. University 2012 focuses on those areas which according to the self-assessment can improve. The objective of University 2012 has been defined as:
To be able to achieve this objective, a new University model will be implemented. This new model will focus on:
Moving to Role Based Curriculums in order to be closer to our people and better support development of their careers;
Ensuring that the Global Curriculum focuses on the content that is federated across the Group and Group initiatives;
Establishing clear learning paths that combine all methods of learning (virtual, on-the-job, classroom) that create stimulating journeys for our people to reinforce the Capgemini Group spirit and values;
Becoming “One Team” (University, HR, Learning & Development) towards participants and the business to be more client centric;
Putting into place industrialized core learning processes and tools with a Rightshore approach in order to maximize the learning spend within and across the Group.
To create closer connections between the University and our people, the business and HR in order to maximise return on our learning investment

## Slide 4
Organisation Chart of the Transformation Project
Capgemini University 2012
3
To achieve the objectives mentioned on the previous page, the project has been divided in 3 streams: University Management, 2012 To-Be and Processes and Existing Projects.
The change of school based curriculum to role based curriculum will have consequences for how the University is organised. The first stream, University Management, focuses on building a new organization structure and a suitable governance model . Within this stream there is also the responsibility to build a strong economic model for the University which focuses on finding a balance between the University offerings .
The sub stream 2012 To-Be and Processes focuses on Next Generation Learning. In first instance the focus for this stream is on creating a pilot for the GEO course during the BPW in October. The pilot will give the team the opportunity to try new techniques and learning methods. For this stream Jacques Birol has been asked to work with our team. Jacques’s expertise is on innovation and has worked for Capgemini before.
Within the stream of Existing Projects the focus is on how the day to day work of the University can transform smoothly into the new organization structure.
The project management is in the hands of Simone Kraal and Karan Kalra. A short introduction will be given by them on the next page.
N.B. The Organization Chart of the University Transformation project is not an iteration of the future organization of the University.

## Slide 5
Introducing the Project Management team
Capgemini University 2012
4
Karan Kalra I am an MBA in Marketing with over 6 years experience in the service industry. I have been with Capgemini for a year and a half as a Senior Consultant with Capgemini India’s Marketing, Sales & Service (MSS) consulting practice. I have just returned from a 6 month secondment in the UK where I worked on an education sector project for most of my time.
My focus within this project is on the stream of Existing Projects.
Simone Kraal I have been working for Capgemini Consulting for two years now. My home office is in the Netherlands where I work for the HR Transformation practice. My last assignment has been for the Dutch Railways who is digitalising their HR processes. Last year I have also had the opportunity to work for the Capgemini Design Center.
For this project I will be supporting Steven on two streams: University Management and 2012 To-Be and Processes.
The project was kicked off with Guillaume Roudil as the Project Manager. As of the beginning of May this year, Guillaume rotated back into the UK Consulting Practice. Simone Kraal and Karan Kalra have been taken over his work. Below you can find a short introduction of both of them.
Although Simone and Karan have divided up the work, you can approach either of them for any of your questions about the project. Simone and Karan have regular meetings to maintain an overview of what is going on within the project.

## Slide 6
Status update
Capgemini University 2012
5
To give you an insight into the progress which has been made in the last quarter, an overview is given per stream.
Project Management:
Reporting structure has been set up within the Transformation Project. On a weekly basis an update is given by the sub-streams
Communication plan has been made to inform key stakeholder groups about the progress of the Transformation Project. This news letter is part of the communication plan
University Management:
    A new high level organisational model for the University has been worked on by Steven, Laurence, Jeremy and Francois. It has been presented to and signed off by Alain. A new core team is being put together to work on the next level of detail.
    The economic model focused around E-learning has been made. Alain Donzeaud has signed the economic model off. Next step is to include Central delivery and Local delivery into the model. It will be presented to Nicolas Dufourcq on July 26.
2012 To Be and Processes:
    Jacques Birol has written a focus document on Next Generation Learning. This has been presented to Alain Donzeaud in June. Within this line of thought Alain requested the next step to be a pilot where new techniques can be tried and evaluated. The course Global Executive Orientation (GEO) will be used as a pilot. This course is scheduled during the BPW in October 2010.

## Slide 7
Status update (contd.)
Existing Projects:
One Business Partner Learning Journey – The first workshop gaining buy-in and enabling L&D Directors has been completed. Business leaders will now be invited to the learning plan presentations and the Learning Plan Tool V2 will be built and piloted with FS.
Global Curriculum – A clear view of the as-is has been consolidated and distributed to all curriculum directors. This would be published on the university site and validated by Steven during the H1 Review. The Governance Model has also been finalized.
Delivery Mix – The possibilities of virtualization and curriculum taxonomy have been completed. Work on the optimal delivery mix has begun and will be consolidated during the week of the H1 review.
Learning Administration – The To-Be University Processes for Enrollment, Program Preparation/ Execution Support and Post-Program Support are being defined. These are expected by 31 July 2010. This will be followed by a gap analysis with the existing SOP and implementation of changes.
Learning Material Production and Standards – E-learning and virtual learning development and deployment process and guidelines are currently in production. This will be followed by a similar exercise for classroom delivery and development of branding guidelines and learning material lifecycle management for all three learning modes.
Marketing and Communications – Design guidelines for the regional MyLearning websites have been created and a process for managing changes to the University and MyLearning sites is being created.
My Learning – A draft POV on curriculum framework and MyLearning standards confirming reporting and visualization requirements is in progress. The first run of curriculum reports is expected by the end of October 2010.
Reporting and Standards – Reporting metrics agreed upon and stakeholder groups for reporting defined. Reporting process and team to be expected in place by the end of 2010.

## Slide 8
H1 Review
As you are already aware, the University H1 Review is coming up on the 19th and 20th July. Day 2 of the review (Tuesday,
20th July) focuses on the transformation project. This would give you an opportunity to understand more about the project.
The agenda for this day is as follows:
08.30 – 09.10 Team Building Activity (Karan, Simone)
09.10 – 10.30 Introduction to University 2012
09.10 – 09.20 Keynote Address from Project Sponsor (Steven)
09.20 – 09.40 Overview of University Management and 2012 To-Be streams (Steven)
09.40 – 10.30 Overview of Existing Projects (Marijke, Regis)
10.30 – 10.45 COFFEE BREAK
10.45 – 11.15 Next Generation Learning (Ling Sian, Aarti, Amit)
11.15 – 12.15 Virtual Learning (Shiva)
12.15 – 13.00 LUNCH
13.00 – 14.00 Workshop on RACI and Role Descriptions for Challenge Align (Account Management), and how this links to the New Organization Structure (University Management) (Marijke, Andrew)
14.00 – 14.30 COFFEE BREAK
14.30 – 15.00 Learning Administration (Abinash, Manasi)
15.00 – 15.30 My Learning (Debbie)
15.30 – 16.00 Wrap up and next steps
We look forward to your participation in the activities and updates of the Transformation project!